## Sheet1
Week | Dates | Deliverables
Week 1 | 03-07-2018 to 03-13-2018 | Project proposal
Week2 | 03-13-2018 to 03-20-2018 | Collecting data and organising in our github repository. Data cleansing and clean data loading into jupyter notebook.
Week 3 | 03-20-2018 to 03-27-2018 | Data visuvalisation and showing the confidential data through visuvalisation in jupyter notebook. Exploring the trends in the data and finding the predictors for different models as per the visuvalisation results.
Week 4 | 03-27-2018 to 04-03-2018 | Performing different unsupervised learning and clustering methods to find the general trend in data and finding the best predictor of the target variables and target results.
Week 5 | 04-03-2018 to 04-10-2018 | Performing different supervised learning of different numeric prediction methods to find the general trend in data and finding the best value of the target results according to metric results . Perform multiple regression analysis and find best target prediction result.
Week 6 | 04-10-2018 to 04-17-2018 | Performing different supervised learning of different classification prediction methods to find the effect of injury, effect of each player practise as the game day approaches. Prediction of better performance based on various factord.Effect of different predictors based on the classification result.
Week 7 | 04-17-2018 to 04-24-2018 | Final documentaition of the project and the best prediction results as per classification,clustering and numeric prediction.